## Gantt Chart
Project ID | [6 empty] | Planned |  | Actual |  | % | Show Gantt for | [5 empty] | Planned | [5 empty] | Show Status? |  |  |  |  | • |  |  |  | What is current Day? | [8 empty] | 31
ID | Level | List of Activties | Resource Assigned | Predecessors | Month | Ong | Start | Dur | Start | Dur | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | 1 | Activities prior to Good Stable Protocol |  |  | Oct-17 | N | 16 | 11 |  |  | 0%
2 | 2 | Draft of Protocol (CSP) | Clinical Manager,Study Lead |  | May-17 | N | 4 | 1 |  |  | 0%
3 | 2 | Study Kick off meeting | CPL,Study Lead,DMTL,MM,SAS Programmer,SDM,STAT PROG,STATS,Clinical Manager | 2 | Oct-17 | N | 17 | 1 |  |  | 0%
4 | 2 | eCRF Requirements Document (RD) Creation | SDM | 3 | Oct-17 | N | 17 | 10 |  |  | 0%

## Legend
| Types of Gantt | Symbols to be used for % complete | 1900-01-30
| Planned | █
Level | Actual | ↓
Note on E5: This one lets you disable the completion status